## Team1_Estimated_Effort
Task Name: | [8 empty] | Rasool | Onel | Michael | Ethan | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Documentation | [8 empty] | Rasool | Onel | Michael | Ethan
| Architecture |  |  |  |  | 2 |  | 5.25 | 1.5 | 1.5 | 0.25 | 2 | 5.25
x |  | Design architecture | Database Designer | Rasool Abbas, Onel Jimenez, Michael Mcfarlin Ethan Wharton | 2 |  | 5.25 |  | 1.5 | 1.5 | 0.25 | 2 | 5.25
| Requirements |  |  |  |  | 9 |  | 8.5 | 0.5 | 5 | 0.5 | 2.5 | 8.5
x |  | Gather | Requirements Engineer | Rasool Abbas, Onel Jimenez, Michael Mcfarlin, Ethan Wharton | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
x |  | Analyze | Requirements Engineer | Onel Jimenez, Ethan Wharton | 4 |  | 4 |  |  | 3 |  | 1 | 4
x |  | Specify | Requirements Engineer | Onel Jimenez, Ethan Wharton | 3 |  | 2.5 |  |  | 1.5 |  | 1 | 2.5
| Documentation |  |  |  |  | 35 |  | 55 | 1.5 | 33.5 | 0.5 | 19.5 | 55
|  | Presentation | Project Manager | Onel Jimenez, Rasool Abbas, Michael Mcfarlin, Ethan Wharton | 2 |  | 6 |  | 0.5 | 4 | 0.5 | 1 | 6
|  | Test Scenario Design | Project Manager | Ethan Wharton | 2 |  | 6 |  |  |  |  | 6 | 6
|  | Requirements Document | Requirements Engineer | Onel Jimenez | 10 |  | 11 |  |  | 11 |  |  | 11
|  | Project Plan | Developer | Ethan Wharton, Onel Jimenez | 5 |  | 11 |  | 0 | 6 |  | 5 | 11
|  | Architecture Document | Architect | Ethan Wharton, Rasool Abbas, Onel Jimenez | 4 |  | 8.5 |  | 0.5 | 2 |  | 6 | 8.5
|  | Test Documentation | Testing Engineer | Onel Jimenez, Ethan Wharton | 8 |  | 5.5 |  |  | 4.5 |  | 1 | 5.5
|  | Time Sheet Management | Project Manager | Onel Jimenez | 0 |  | 2.5 |  |  | 2.5 |  |  | 2.5
|  | User Guide | Developer, Requirements Engineer | Onel Jimenez, Rasool Abbas | 4 |  | 4.5 |  | 0.5 | 3.5 |  | 0.5 | 4.5
Development and Implementation | Design |  |  |  |  | 14 |  | 31.5 | 0 | 0 | 23.5 | 8 | 31.5
|  | Create UI design for Login/Register pages | Developer | Michael McFarlin, Ethan Wharton | 1 |  | 4 |  |  |  | 3 | 1 | 4
|  | Create UI design for Dashboard page | Developer | Michael McFarlin, Ethan Wharton | 5 |  | 10.5 |  |  |  | 8.5 | 2 | 10.5
|  | Create UI design for My Fundraisers page | Developer | Michael McFarlin, Ethan Wharton | 5 |  | 9 |  |  |  | 7 | 2 | 9
|  | Create UI design for Settings page | Developer | Michael McFarlin, Ethan Wharton | 3 |  | 5 |  |  |  | 3 | 2 | 5
|  | Other UI design work (Dropdowns/windows/page differences) | Developer | Michael McFarlin, Ethan Wharton | 0 |  | 3 |  |  |  | 2 | 1 | 3
| Development |  |  |  |  | 170 |  | 228 | 168 | 11 | 28 | 21 | 228
|  | Determine technology needs | Developer | Rasool Abbas | 15 |  | 13 |  | 5 | 2 | 1 | 5 | 13
|  | Research and learn new language and environment | Developer | Rasool Abbas, Michael Mcfarlin, Ethan Wharton | 20 |  | 43 |  | 15 |  | 22 | 6 | 43
|  | Develop Front End | Developer | Rasool Abbas, Ethan Wharton | 25 |  | 28 |  | 26 |  |  | 2 | 28
|  | Develop Back End | Developer | Rasool Abbas | 25 |  | 21 |  | 21 |  |  |  | 21
|  | Implement Database | Developer | Rasool Abbas, Onel Jimenez | 25 |  | 24 |  | 22 | 2 |  |  | 24
|  | Password Recovery | Developer | Rasool Abbas | 15 |  | 19 |  | 19 |  |  |  | 19
|  | Picture Upload | Developer | Rasool Abbas | 15 |  | 20 |  | 20 |  |  |  | 20
|  | Deployment | Developer | Rasool Abbas, Onel Jimenez, Michael Mcfarlin, Ethan Wharton | 10 |  | 27 |  | 10 | 7 | 5 | 5 | 27
|  | Unit Testing | Developer | Rasool Abbas | 20 |  | 33 |  | 30 |  |  | 3 | 33
| Analysis |  |  |  |  | 54 |  | 46.1 | 13.5 | 12.5 | 10 | 10.1 | 46.1
|  | System Testing | Tester | Rasool Abbas, Onel Jimenez | 2 |  | 3 |  | 1 | 2 |  |  | 3
|  | Bug fix as required | Tester, Developer | Rasool Abbas | 5 |  | 1 |  | 1 |  |  |  | 1
|  | Evaluate needs for next iteration | Project Manager | Rasool Abbas, Onel Jimenez, Michael Mcfarlin Ethan Wharton | 40 |  | 40 |  | 10 | 10 | 10 | 10 | 40
|  | Acceptance Testing | Tester, Project Manager | Rasool Abbas, Onel Jimenez | 2 |  | 1.5 |  | 1 | 0.5 |  |  | 1.5
|  | Bug fix as required | Tester, Developer | Rasool Abbas, Ethan Wharton | 5 |  | 0.6 |  | 0.5 |  |  | 0.1 | 0.6
Total |  |  |  |  | 284 | 284 | 374.35 | 374.35 | 185 | 63.5 | 62.75 | 63.1 | 374.35